## Sheet1
Route | Status | Total Stop Count | Unchanged Route Panel Unchanged Location | Unchanged Location | Route Panel Changes | Removed Stops | Weighted Score
RTO | COMPLETE | NA | NA | NA | NA | NA | NA
198 | SIGNS ORDERED | 21 | 21 | 21 | 0 | 0 | 100%
197 | APPROVED / SIGNS NOT ORDERED | 45 | 44 | 45 | 1 | 0 | 99.26%
800 | SIGNS ORDERED | 42 | 39 | 42 | 3 | 0 | 97.62%
194 | PUNCH | 96 | 92 | 94 | 4 | 2 | 97.22%
195 | SIGNS ORDERED | 52 | 47 | 52 | 5 | 0 | 96.79%
196 | SIGNS ORDERED | 63 | 56 | 63 | 7 | 0 | 96.3%
39 | INSTALL IN PROGRESS | 89 | 77 | 88 | 12 | 1 | 94.76%
85 | APPROVED / SIGNS NOT ORDERED | 87 | 72 | 87 | 15 | 0 | 94.25%
162 | SIGNS ORDERED | 31 | 23 | 31 | 8 | 0 | 91.4%
5 | SIGNS ORDERED | 102 | 68 | 100 | 34 | 2 | 87.58%
83 | SIGNS ORDERED | 81 | 49 | 81 | 32 | 0 | 86.83%
78 | INSTALL IN PROGRESS | 53 | 28 | 53 | 25 | 0 | 84.28%
192 | APPROVED / SIGNS NOT ORDERED | 67 | 55 | 56 | 12 | 11 | 83.08%
55 | MARTA REVIEWING ART | 135 | 92 | 116 | 43 | 19 | 80%
191 | SIGNS ORDERED | 145 | 56 | 145 | 89 | 0 | 79.54%
193 | SIGNS ORDERED | 181 | 87 | 168 | 94 | 13 | 77.9%
110 | APPROVED / SIGNS NOT ORDERED | 98 | 35 | 96 | 63 | 2 | 77.21%
116 | SIGNS ORDERED | 84 | 38 | 78 | 46 | 6 | 76.98%
180 | PUNCH | 96 | 30 | 95 | 66 | 1 | 76.39%
119 | SIGNS ORDERED | 64 | 26 | 59 | 38 | 5 | 75%
87 | SIGNS ORDERED | 69 | 29 | 63 | 40 | 6 | 74.88%
125 | APPROVED / SIGNS NOT ORDERED | 106 | 32 | 102 | 74 | 4 | 74.21%
115 | PUNCH | 118 | 34 | 114 | 84 | 4 | 74.01%
95 | SIGNS ORDERED | 82 | 16 | 82 | 66 | 0 | 73.17%
32 | IN REVISION | 107 | 33 | 98 | 74 | 9 | 71.34%
71 | IN REVISION | 97 | 12 | 97 | 85 | 0 | 70.79%
132 | SIGNS ORDERED | 59 | 37 | 44 | 22 | 15 | 70.62%
117 | SIGNS ORDERED | 179 | 27 | 172 | 152 | 7 | 69.09%
120 | COMPLETE | 94 | 0 | 94 | 94 | 0 | 66.67%
74 | MARTA REVIEWING ART | 74 | 23 | 62 | 51 | 12 | 66.22%
60 | MARTA REVIEWING ART | 62 | 0 | 61 | 62 | 1 | 65.59%
25 | APPROVED / SIGNS NOT ORDERED | 45 | 0 | 44 | 45 | 1 | 65.19%
89 | SIGNS ORDERED | 116 | 26 | 100 | 90 | 16 | 64.94%
185 | SIGNS ORDERED | 74 | 26 | 59 | 48 | 15 | 64.86%
12 | SIGNS ORDERED | 90 | 1 | 87 | 89 | 3 | 64.81%
114 | IN REVISION | 94 | 0 | 91 | 94 | 3 | 64.54%
124 | APPROVED / SIGNS NOT ORDERED | 83 | 0 | 80 | 83 | 3 | 64.26%
107 | SIGNS ORDERED | 122 | 0 | 116 | 122 | 6 | 63.39%
165 | IN REVISION | 61 | 20 | 48 | 41 | 13 | 63.39%
153 | APPROVED / SIGNS NOT ORDERED | 20 | 0 | 19 | 20 | 1 | 63.33%
86 | MARTA REVIEWING ART | 137 | 0 | 128 | 137 | 9 | 62.29%
15 | IN REVISION | 148 | 0 | 132 | 148 | 16 | 59.46%
121 | SIGNS ORDERED | 127 | 11 | 106 | 116 | 21 | 58.53%
4 | IN REVISION | 110 | 41 | 76 | 69 | 34 | 58.48%
186 | INSTALL IN PROGRESS | 78 | 0 | 68 | 78 | 10 | 58.12%
79 | IN REVISION | 73 | 19 | 54 | 54 | 19 | 57.99%
123 | MARTA REVIEWING ART | 7 | 0 | 6 | 7 | 1 | 57.14%
47 | APPROVED / SIGNS NOT ORDERED | 79 | 0 | 67 | 79 | 12 | 56.54%
81 | IN REVISION | 136 | 61 | 83 | 75 | 53 | 55.64%
21 | INSTALL IN PROGRESS | 107 | 26 | 76 | 81 | 31 | 55.45%
14 | MARTA REVIEWING ART | 56 | 18 | 37 | 38 | 19 | 54.76%
104 | SIGNS ORDERED | 21 | 8 | 13 | 13 | 8 | 53.97%
50 | APPROVED / SIGNS NOT ORDERED | 110 | 0 | 89 | 110 | 21 | 53.94%
36 | IN REVISION | 114 | 0 | 92 | 114 | 22 | 53.8%
75 | IN REVISION | 86 | 0 | 69 | 86 | 17 | 53.49%
73 | SIGNS ORDERED | 109 | 0 | 86 | 109 | 23 | 52.6%
66 | MARTA REVIEWING ART | 135 | 15 | 98 | 120 | 37 | 52.1%
181 | SIGNS ORDERED | 150 | 0 | 117 | 150 | 33 | 52%
3 | SIGNS ORDERED | 93 | 13 | 64 | 80 | 29 | 50.54%
1 | IN REVISION | 75 | 11 | 50 | 64 | 25 | 49.33%
34 | MARTA REVIEWING ART | 109 | 23 | 67 | 86 | 42 | 48.01%
141 | APPROVED / SIGNS NOT ORDERED | 72 | 0 | 50 | 72 | 22 | 46.3%
37 | IN REVISION | 61 | 0 | 42 | 61 | 19 | 45.9%
140 | SIGNS ORDERED | 54 | 0 | 37 | 54 | 17 | 45.68%
111 | MARTA REVIEWING ART | 98 | 0 | 67 | 98 | 31 | 45.58%
172 | SIGNS ORDERED | 114 | 0 | 76 | 114 | 38 | 44.44%
82 | INSTALL IN PROGRESS | 82 | 0 | 54 | 82 | 28 | 43.9%
51 | APPROVED / SIGNS NOT ORDERED | 86 | 0 | 56 | 86 | 30 | 43.41%
103 | SIGNS ORDERED | 71 | 0 | 46 | 71 | 25 | 43.19%
126 | MARTA REVIEWING ART | 85 | 0 | 52 | 85 | 33 | 40.78%
49 | APPROVED / SIGNS NOT ORDERED | 100 | 0 | 61 | 100 | 39 | 40.67%
6 | IN REVISION | 118 | 0 | 71 | 118 | 47 | 40.11%
93 | MARTA REVIEWING ART | 45 | 0 | 27 | 45 | 18 | 40%
832 | MARTA REVIEWING ART | 46 | 0 | 27 | 46 | 19 | 39.13%
84 | SIGNS ORDERED | 36 | 6 | 18 | 30 | 18 | 38.89%
102 | IN REVISION | 28 | 0 | 16 | 28 | 12 | 38.1%
42 | MARTA REVIEWING ART | 103 | 16 | 50 | 87 | 53 | 37.54%
26 | APPROVED / SIGNS NOT ORDERED | 96 | 0 | 51 | 96 | 45 | 35.42%
178 | APPROVED / SIGNS NOT ORDERED | 49 | 16 | 17 | 33 | 32 | 34.01%
813 | APPROVED / SIGNS NOT ORDERED | 57 | 0 | 29 | 57 | 28 | 33.92%
825 | MARTA REVIEWING ART | 26 | 0 | 13 | 26 | 13 | 33.33%
19 | MARTA REVIEWING ART | 127 | 0 | 61 | 127 | 66 | 32.02%
816 | IN REVISION | 71 | 0 | 33 | 71 | 38 | 30.99%
8 | MARTA REVIEWING ART | 117 | 0 | 54 | 117 | 63 | 30.77%
850 | APPROVED / SIGNS NOT ORDERED | 73 | 0 | 32 | 73 | 41 | 29.22%
809 | MARTA REVIEWING ART | 82 | 0 | 35 | 82 | 47 | 28.46%
183 | SIGNS ORDERED | 40 | 0 | 17 | 40 | 23 | 28.33%
9 | MARTA REVIEWING ART | 111 | 0 | 45 | 111 | 66 | 27.03%
189 | MARTA REVIEWING ART | 83 | 0 | 33 | 83 | 50 | 26.51%
68 | MARTA REVIEWING ART | 121 | 0 | 45 | 121 | 76 | 24.79%
867 | MARTA REVIEWING ART | 58 | 0 | 20 | 58 | 38 | 22.99%
24 | APPROVED / SIGNS NOT ORDERED | 188 | 0 | 63 | 188 | 125 | 22.34%
2 | IN REVISION | 56 | 0 | 18 | 56 | 38 | 21.43%
94 | APPROVED / SIGNS NOT ORDERED | 32 | 0 | 10 | 32 | 22 | 20.83%
865 | SIGNS ORDERED | 71 | 0 | 22 | 71 | 49 | 20.66%
150 | MARTA REVIEWING ART | 52 | 0 | 16 | 52 | 36 | 20.51%
856 | SIGNS ORDERED | 65 | 0 | 20 | 65 | 45 | 20.51%
155 | MARTA REVIEWING ART | 88 | 0 | 27 | 88 | 61 | 20.45%
58 | IN REVISION | 117 | 0 | 34 | 117 | 83 | 19.37%
899 | IN REVISION | 22 | 0 | 6 | 22 | 16 | 18.18%
40 | APPROVED / SIGNS NOT ORDERED | 66 | 0 | 13 | 66 | 53 | 13.13%
27 | APPROVED / SIGNS NOT ORDERED | 68 | 0 | 11 | 68 | 57 | 10.78%
853 | IN REVISION | 56 | 0 | 9 | 56 | 47 | 10.71%
143 | SIGNS ORDERED | 34 | 0 | 5 | 34 | 29 | 9.804%
30 | APPROVED / SIGNS NOT ORDERED | 99 | 0 | 13 | 99 | 86 | 8.754%
133 | APPROVED / SIGNS NOT ORDERED | 51 | 0 | 3 | 51 | 48 | 3.922%
148 | APPROVED / SIGNS NOT ORDERED | 35 | 0 | 1 | 35 | 34 | 1.905%
823 | SIGNS ORDERED | 61 | 0 | 1 | 61 | 60 | 1.093%
142 | IN REVISION | 25 | 0 | 0 | 25 | 25 | 0%
188 | MARTA REVIEWING ART | 23 | 0 | 0 | 23 | 23 | 0%
201 | #N/A (Not in Tracker sheet) | 2 | 0 | 0 | 2 | 2 | 0%
221 | SIGNS ORDERED | 8 | 0 | 0 | 8 | 8 | 0%
295 | IN REVISION | 2 | 0 | 0 | 2 | 2 | 0%

## Sheet2
Priority | Route | route meshed | Project Number | PM | Number of Stops | Walton Check for Duplicates | Qty of Shared Stops | Has Stops Under Construction | Stop Missing - QTY | New 101 Poles | New 102 Posts (QTY) | Notes | Project Status | Ball in Court | Installer | Art Revisions Submitted to Design (Date) | Art Ready for MARTA Approval | Date Art Ready for MARTA Approval | Art Ready for Marta Approval Count | Art Revisions Submitted to Marta Date | Run Book Through Sherlock | MARTA Comments rec'd | MARTA Approved | Route Locked | SO Setup | Sign Order Placed | Date Sign Ordered | Signs Ordered Count | Submitted Hardware to Order | Re-Order BD Brackets | Hardware Expected Date | Actual Hardware Ship | Estimated Delivery Date (Hardware) | Hardware Tracking | Submitted to Spencer ¦ Bowstone | Expected Spencer ¦ Bowstone | Actual Ship Date (Bracket) | Expected Delivery Date (Brackets) | Spencer/Bowstone Tracking | Submitted to Engrave-Tech | Expected Engrave-Tech Completion Date | Projected Panel Ship Date (Signage) | Actual Panel Ship Date (Signage) | Estimated Delivery Date (Signage) | Engrave-Tech Tracking | Product Arrived at Installer | Pre 811 Planned Mark Date | Call 811 | 811 Marked Date | Install Planned Date | Installation Start Date | Installation Completion Date | Ready for Inspection | Punch | Has Returned Product | Punch Complete | Ready for Billing | Submitted for billing | DNU
1 | 115 | TRUE | PR316139 | JESSE BARRY | 116 | TRUE |  |  |  |  | 17 | 12/5/23 (JB): (84) stops ready for inspection. See filter in route (31) stops incomplete (1) of the incomplete stops is pending a 101 pole Misplaced PIP's reordered. Shipping 12/15 | PUNCH | WALTON - JESSE | Cardinal Concrete | 2023-04-19 | TRUE | 2023-09-26 | YES | 2023-04-21 | FALSE |  | 2023-04-27 | TRUE | 2023-04-28 | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-23 |  |  |  | 2023-05-02 | 2023-05-30 | 2023-06-01 | 2023-06-02 | 13088468-7 | 2023-05-02 | 2023-05-30 | 2023-07-14 | 2023-07-14 | 2023-07-17 | 27659067-8 / PRO 116931485 |  | 2023-07-03 |  |  | 2023-07-24 | 2023-07-24 | 2023-09-11 |  | TRUE | TRUE
1 | 162 | TRUE | PR316223 | JESSE BARRY | 30 | TRUE | 21 |  |  |  | 2 | 11/13/23 (JB): Pending installation schedule from Blackjack | SIGNS ORDERED | WALTON - JESSE | C. Robertson | 2023-04-19 | TRUE | 2023-09-26 | YES | 2023-03-30 | FALSE |  | 2023-04-27 | TRUE | 2023-04-28 | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-23 |  |  |  | 2023-04-28 | 2023-05-29 | 2023-06-01 | 2023-06-02 | 13088467-8 | 2023-04-28 | 2023-05-29 | 2023-06-16 | 2023-06-21 | 2023-06-23 | SEFL 116755229 |  | 2023-09-11 |  |  | 2023-10-02
1 | 180 | TRUE | PR316227 | JESSE BARRY | 95 | TRUE |  |  |  |  | 9 | 12/5/23 (JB): (91) stops ready for inspection. See filter in route (3) stops incomplete Misplaced PIP's reordered. Shipping 12/15 | PUNCH | WALTON - JESSE | Cardinal Concrete | 2023-04-19 | TRUE | 2023-09-26 | YES | 2023-04-21 | FALSE | 2023-04-26 | 2023-04-28 | TRUE | 2023-05-03 | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-23 |  |  |  | 2023-05-02 | 2023-05-30 | 2023-06-01 | 2023-06-02 | 13088468-7 | 2023-05-02 | 2023-05-30 | 2023-06-26 | 2023-06-26 | 2023-06-28 | SEFL 31061126-1 / PRO 116794976 |  | 2023-07-17 |  |  | 2023-08-07 | 2023-08-07 |  |  | TRUE
1 | 194 | TRUE | PR316238 | JESSE BARRY | 94 | TRUE |  |  |  |  | 6 | 12/5/23 (JB): (90) stops ready for inspection. See filter in route (4) stops incomplete New PIP's ordered. Shipping 12/15 Misplaced PIP's reordered. Shipping 12/15 | PUNCH | WALTON - JESSE | Cardinal Concrete | 2023-04-19 | TRUE | 2023-09-26 | YES | 2023-05-09 | FALSE |  | 2023-04-27 | TRUE | 2023-05-05 | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-23 |  |  |  | 2023-05-05 | 2023-06-05 | 2023-06-01 | 2023-06-02 | 13088468-7 | 2023-05-05 | 2023-06-05 | 2023-06-27 | 2023-06-27 | 2023-06-29 | SEFL 31063253-6 / PRO 116805854 |  | 2023-07-10 |  |  | 2023-07-31 | 2023-07-31 | 2023-09-12 |  | TRUE | TRUE
1 | 83 | TRUE | PR316163 | JESSE BARRY | 80 | TRUE |  |  |  |  | 18 | 11/13/23 (JB): Pending installation schedule from Blackjack | SIGNS ORDERED | WALTON - JESSE | C. Robertson | 2023-03-13 | TRUE | 2023-09-26 | YES | 2023-03-30 | FALSE |  | 2023-04-27 | TRUE | 2023-05-11 | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-23 |  |  |  | 2023-05-11 | 2023-06-01 | 2023-06-01 | 2023-06-02 | 13088467-8 | 2023-05-11 | 2023-06-01 | 2023-07-12 | 2023-07-12 | 2023-07-14 | SEFL 27659066-0 / PRO 116910453 |  | 2023-09-18 |  |  | 2023-10-09
1 | 221 | TRUE | PR316244 | Kelly Stock | 6 | TRUE |  |  |  |  | 1 | Install PO complete to Blackjack 8/30/23: | SIGNS ORDERED | WALTON - KELLY | C. Robertson | 2023-02-27 | TRUE | 2023-09-26 | YES | 2023-02-27 | FALSE | 2022-05-23 | 2023-04-27 | TRUE | 2023-04-28 | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-16 |  |  |  | 2023-04-28 | 2023-05-29 | 2023-06-01 | 2023-06-02 | 13088467-8 | 2023-04-28 | 2023-05-29 | 2023-06-07 | 2023-06-07 | 2023-06-12 | UPS 1Z4152380397427726 |  | 2023-08-28 |  |  | 2023-09-18
1 | 39 | TRUE | PR316207 | Kelly Stock | 85 | TRUE |  | TRUE |  |  | 11 | 5/22/23: Signs Ordered | INSTALL IN PROGRESS | WALTON - KELLY | Cardinal Concrete | N/A | TRUE | 2023-09-26 | YES | 2023-02-27 | FALSE | N/A | 2022-06-06 | TRUE |  | TRUE | 2023-09-26 | X | TRUE |  | 2023-05-30 |  |  |  | 2023-03-30 | 2023-04-27 | 2023-06-01 | 2023-06-02 | 13088468-7 | 2023-03-30 | 2023-04-27 |  | 2023-05-30 | 2023-06-01 | SEFL 28902415-3 |  | 2023-05-22 |  |  | 2023-06-12 | 2023-06-12 |  |  |  | TRUE
1 | 800 | TRUE | PR316179 | Kelly Stock | 41 |  |  | TRUE |  |  | 5 | Install PO complete to Blackjack 8/30/23: TB shipping today | SIGNS ORDERED | WALTON - KELLY | C. Robertson | 2023-03-15 | TRUE | 2023-09-26 | YES | 2023-05-03 | FALSE |  | 2023-05-04 | TRUE |  | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-16 |  |  |  | 2023-05-11 | 2023-06-08 | 2023-06-01 | 2023-06-02 | 13088467-8 | 2023-05-11 | 2023-06-08 | 2023-06-15 | 2023-06-21 | 2023-06-23 | SEFL 116755229 |  | 2023-08-28 |  |  | 2023-09-18
1 | 82 | TRUE | PR316172 | Kelly Stock | 80 | TRUE |  |  |  |  | 22 | 5/22/23: Signs ordered; correcting PO quantities | INSTALL IN PROGRESS | WALTON - KELLY | Black Jack Paving | 2023-05-03 | TRUE | 2023-09-26 | YES | 2023-05-26 | FALSE |  | 2023-05-04 | TRUE |  | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-16 |  |  |  | 2023-05-11 | 2023-06-08 | 2023-06-01 | 2023-06-02 | 13088467-8 | 2023-05-11 | 2023-06-08 | 2023-06-28 | 2023-06-29 | 2023-07-03 | SEFL 28461007-1 / PRO 116828498 |  | 2023-08-28 |  |  | 2023-09-18 | 2023-09-19
1 | 95 | TRUE | PR316115 | Kelly Stock | 82 | TRUE |  |  |  |  | 25 | Install PO complete to Blackjack 5/5/23: No comments; set up SO | SIGNS ORDERED | WALTON - KELLY | C. Robertson | 2023-04-19 | TRUE | 2023-09-26 | YES | 2023-04-28 | FALSE | 2023-05-05 | 2023-05-05 | TRUE | 2023-05-26 | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-16 |  |  |  | 2023-05-26 | 2023-06-23 | 2023-07-12 | 2023-07-13 | BOL# 11060A | 2023-05-26 | 2023-06-23 | 2023-07-18 | 2023-07-19 | 2023-07-24 | SEFL 31063281-1 / PRO 116966386 / UPS 1Z4152380399353712 (large route panel)
1 | RTO |  | PR316651 | Kelly Stock | 58 | TRUE |  |  |  |  | 47 |  | COMPLETE | WALTON - KELLY | Supreme | N/A | TRUE | 2023-09-26 | YES | N/A | FALSE | N/A | 2022-06-03 | TRUE |  | TRUE | 2023-09-26 | X | TRUE |  | 2023-09-04 | N/A |  |  | 2022-06-15 | 2022-07-13 | N/A | N/A | N/A | 2022-06-10 | 2022-07-22 | N/A | 2022-08-19 | 2023-09-04 | N/A | 2022-08-26 | 2022-12-16 | N/A | N/A | 2023-01-06 | 2023-01-06 | 2023-03-10 |  | TRUE
2 | 186 | TRUE | PR316231 | JESSE BARRY | 79 | TRUE | 4 |  |  |  | 10 | 11-30 (SR)Install PO252612 - ready to be sent in folder 11/13/23 (JB): Pending installation schedule from Cardinal Concrete | INSTALL IN PROGRESS | WALTON - JESSE | Cardinal Concrete | 2023-05-08 | TRUE | 2023-09-26 | YES | 2023-05-09 | FALSE | 2023-04-26 | 2023-05-24 | TRUE | 2023-05-30 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-14 |  |  |  | 2023-06-02 | 2023-06-30 | 2023-07-12 | 2023-07-13 | BOL# 11060B | 2023-06-02 | 2023-06-30 | 2023-08-02 | 2023-08-02 | 2023-08-04 | SEFL 29189026-1 / PRO 117085049
2 | 193 | TRUE | PR316237 | JESSE BARRY | 159 | TRUE |  |  |  |  | 48 | 11-30 (SR) Install PO252619 - Ready to be sent in folder 11/13/23 (JB): Pending installation schedule from Cardinal Concrete | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-04-20 | TRUE | 2023-09-26 | YES | 2023-04-21 | FALSE | 2023-04-26 | 2023-04-26 | TRUE | 2023-05-26 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-21 |  |  |  | 2023-06-02 | 2023-06-30 | 2023-07-12 | 2023-07-13 | BOL# 11060B | 2023-06-02 | 2023-06-30 | 2023-08-09 | 2023-08-09 | 2023-08-11 | SEFL 31062797-4 / PRO 117142727
2 | 89 | TRUE | PR316125 | JESSE BARRY | 114 | TRUE |  |  |  |  | 38 | 11-30 (SR) Install PO252630 - Ready to be sent in folder 11/13/23 (JB): Pending installation schedule from Cardinal Concrete | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2022-04-19 | TRUE | 2023-09-26 | YES | 2023-04-21 | FALSE | 2023-04-26 | 2023-05-08 | TRUE | 2023-05-26 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-14 |  |  |  | 2023-06-02 | 2023-06-30 | 2023-07-12 | 2023-07-13 | BOL# 11060B | 2023-06-02 | 2023-06-30 | 2023-07-28 | 2023-07-28 | 2023-07-30 | SEFL 31065378-9 / PRO 117048267
2 | 121 | TRUE | PR316153 | Kelly Stock | 123 |  | 1 |  |  |  | 29 | 12-1 (SR) Install PO252683 - ready to be sent in folder 9/27/23: Hardware ordered | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-06-26 | TRUE | 2023-09-26 | YES | 2023-07-07 | FALSE |  | 2023-07-10 | TRUE | 2023-07-26 | TRUE | 2023-09-26 | X |  |  | 2023-10-25 |  |  |  | 2023-07-26 | 2023-08-28 | 2023-08-24 |  | BOL# 11067 | 2023-07-26 | 2023-08-28 | 2023-09-13 | 2023-09-21 | 2023-09-25 | SEFL 32825601-3 / PRO 117505480
2 | 21 | TRUE | PR316243 | Kelly Stock | 106 | TRUE |  |  |  |  | 26 | 12-1 (SR) Install PO252687 -ready to be sent in folder 8/7/23: Need QF quote | INSTALL IN PROGRESS | WALTON - KELLY | Cardinal Concrete | 2023-07-06 | TRUE | 2023-09-26 | YES | 2023-07-07 | FALSE |  | 2023-07-07 | TRUE | 2023-07-10 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-07 |  |  |  | 2023-07-10 | 2023-07-31 | 2023-07-26 | 2023-07-27 | BOL# 11063B | 2023-07-10 | 2023-07-31 | 2023-09-06 | 2023-09-12 | 2023-09-15 | SEFL PRO 117422941 |  | 2023-09-04 |  |  | 2023-09-25 | 2023-09-25
2 | 5 | TRUE | PR316201 | Kelly Stock | 100 | TRUE |  |  |  |  | 23 | 12-1 (SR) Install PO252688 - ready to be sent -in folder 8/7/23: Need QF quote | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-03-24 | TRUE | 2023-09-26 | YES | 2023-06-02 | FALSE |  | 2023-06-15 | TRUE | 2023-07-07 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-14 |  |  |  | 2023-07-10 | 2023-07-31 | 2023-07-26 | 2023-07-27 | BOL# 11063B | 2023-07-10 | 2023-07-31 | 2023-09-01 | 2023-09-08 | 2023-09-11 | SEFL 31065156-5 / PRO 117395668
2 | 78 | TRUE | PR316182 | Kelly Stock | 55 | TRUE |  |  |  |  | 13 | 12-1 (SR) Install PO252689 - ready to be sent - in folder 5/5/23: Marta Approved | INSTALL IN PROGRESS | WALTON - KELLY | Cardinal Concrete | 2023-02-16 | TRUE | 2023-09-26 | YES | 2023-05-03 | FALSE | 2023-05-05 | 2023-05-05 | TRUE | 2023-05-26 | TRUE | 2023-09-26 | X | TRUE |  | 2023-06-16 |  |  |  | 2023-05-26 | 2023-06-23 | 2023-07-12 | 2023-07-13 | BOL# 11060B | 2023-05-26 | 2023-06-23 | 2023-07-21 | 2023-07-21 | 2023-07-26 | SEFL 31063290-1 / PRO 116991305 |  | 2023-07-26 |  |  | 2023-08-16 | 2023-08-16 | 2023-09-08
2 | 191 | TRUE | PR316235 | Sharnee Riley | 138 | TRUE |  |  |  |  | 44 | 11-29 Sub Install PO252449 11-16 Need to order 101 tubes from Spencer 11-16 Need to order 103 strap 11-16: Signs / brackets / hardware all ordered and shipped | SIGNS ORDERED | WALTON - SHARNEE | C. Robertson | 2023-05-03 | TRUE | 2023-09-26 | YES | 2023-06-02 | FALSE |  | 2023-06-29 | TRUE | 2023-07-07 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-07 |  |  |  | 2023-07-10 | 2023-07-31 | 2023-07-26 | 2023-07-27 | BOL# 11063 | 2023-07-10 | 2023-07-31 | 2023-09-08 | 2023-09-07 | 2023-09-11 | SEFL 32825582-3 / PRO 117381501
2 | 73 | TRUE | PR316186 | Sharnee Riley | 107 | TRUE |  |  |  |  | 63 | 11-30 Install PO252662 - Need to sent to vendor 11-29 (SR) req design revision to reflect change to 102 A install for 900975 11/22/23: (KB) Stop 900975 to be replaced by Marta by 12/16 11/13/23 (JB): Pending installation schedule from Cardinal Concrete1 11-16 Sign/ brackets hardware all ordered and shipped | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-05-08 | TRUE | 2023-09-26 | YES | 2023-05-09 | FALSE | 2023-04-26 | 2023-05-24 | TRUE | 2023-05-30 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-11 |  |  |  | 2023-06-02 | 2023-06-30 | 2023-07-12 | 2023-07-13 | BOL# 11060B | 2023-06-02 | 2023-06-30 | 2023-07-28 | 2023-07-28 | 2023-07-30 | SEFL 31065378-9 / PRO 117048267 / UPS 1Z4152380390124628 (large route panels)
3 | 107 | TRUE | PR316129 | JESSE BARRY | 134 |  | 22 |  |  |  | 54 | 12-4 Install PO252737 -ready to be sent - in folder 11/13/23 (JB): Pending installation schedule from Cardinal Concrete | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-07-27 | TRUE | 2023-09-26 | YES | 2023-07-28 | FALSE | 2023-07-20 | 2023-08-02 | TRUE | 2023-08-02 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-28 |  |  |  | 2023-08-04 | 2023-09-01 | 2023-08-24 |  | BOL# 11067 | 2023-08-04 | 2023-09-01 | 2023-11-02 | 2023-11-02 | 2023-11-06 | SEFL PRO 117879266
3 | 12 | TRUE | PR316148 | JESSE BARRY | 82 | [5 empty] | 32 | 12-4 (SR) Install PO252776 - ready to send - in file 11/13/23 (JB): Pending installation schedule from Cardinal Concrete | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-06-22 | TRUE | 2023-09-26 | YES | 2023-06-23 | FALSE | 2023-06-21 | 2023-06-30 | TRUE | 2023-07-05 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-28 |  |  |  | 2023-07-07 | 2023-08-04 | 2023-07-26 | 2023-07-27 | BOL# 11063B | 2023-07-07 | 2023-08-04 | 2023-08-31 | 2023-09-11 | 2023-09-13 | PRO 117411540
3 | 3 | TRUE | PR316250 | JESSE BARRY | 82 | [5 empty] | 19 | 12-4 (SR) Install PO252784 - ready to send - in file 11/13/23 (JB): Pending installation schedule from Cardinal Concrete | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-06-15 | TRUE | 2023-09-26 | YES | 2023-06-19 | FALSE | NA | 2023-06-21 | TRUE | 2023-07-05 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-28 |  |  |  | 2023-07-07 | 2023-08-04 | 2023-07-26 | 2023-07-27 | BOL# 11063B | 2023-07-07 | 2023-08-04 | 2023-08-31 | 2023-09-01 | 2023-09-06 | SEFL 32825754-1 / PRO 328257541
3 | 117 | TRUE | PR316145 | Kelly Stock | 177 |  | 2 |  |  |  | 39 | 12-4 Install PO252785 - ready to send - in file 8/7/23: Signs Ordered; Hardware request submitted | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-07-20 | TRUE | 2023-09-26 | YES | 2023-07-24 | FALSE |  | 2023-08-01 | TRUE | 2023-08-07 | TRUE | 2023-09-26 | X | TRUE |  | 2023-09-05 |  |  |  | 2023-08-07 | 2023-09-05 | 2023-08-24 |  | BOL# 11067 | 2023-08-07 | 2023-09-05 | 2023-10-26 | 2023-10-26 | 2023-10-30 | SEFL PRO 117820440
3 | 181 | TRUE | PR316228 | Kelly Stock | 151 | [5 empty] | 35 | 12-4 INstall PO252787 ready to send - in file 8/7/23: Signs Ordered; Hardware request submitted | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-07-20 | TRUE | 2023-09-26 | YES | 2023-07-07 | FALSE |  | 2023-07-24 | TRUE | 2023-08-07 | TRUE | 2023-09-26 | X | TRUE |  | 2023-09-05 |  |  |  | 2023-08-07 | 2023-09-05 | 2023-08-24 |  | BOL# 11067 | 2023-08-07 | 2023-09-05 | 2023-09-19 | 2023-10-13 | 2023-10-18 | PRO 117711900
3 | 196 | TRUE | PR316240 | Kelly Stock | 59 | [5 empty] | 14 | 12-4 Install PO252795 - ready to send - in file 7/10/23: Signage Ordered | SIGNS ORDERED | WALTON - KELLY | C Robertson | 2023-06-02 | TRUE | 2023-09-26 | YES | 2023-06-29 | FALSE |  | 2023-07-07 | TRUE | 2023-07-10 | TRUE | 2023-09-26 | X | TRUE |  | 2023-10-25 |  |  |  | 2023-07-10 | 2023-07-31 | 2023-07-26 | 2023-07-27 | BOL# 11063 | 2023-07-10 | 2023-07-31 | 2023-08-31 | 2023-09-01 | 2023-09-06 | SEFL 32825755-9 / PRO 117346900
3 | 865 | TRUE | PR316132 | Kelly Stock | 71 |  | 19 |  |  |  | 18 | 12-4 Install PO252792 - ready to send - in file 8/7/23: Need print files, POs ready and Hardware request submitted | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-06-16 | TRUE | 2023-09-26 | YES | 2023-06-27 | FALSE |  | 2023-07-26 | TRUE | 2023-08-07 | TRUE | 2023-09-26 | X | TRUE |  | 2023-09-05 |  |  |  | 2023-08-14 | 2023-09-18 | 2023-08-24 |  | BOL# 11067 | 2023-08-14 | 2023-09-18 | 2023-10-19 | 2023-10-19 | 2023-10-23 | PRO 117750093
3 | 119 | TRUE | PR316146 | Sharnee Riley | 64 | [5 empty] | 8 | 11-17 Install PO252680 - Need to send to vendor 11-17 Need to order straps 11-17 Signs/ brackets and hardware ordered 7/12/23: R7 uploaded for Marta Approval | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-07-07 | TRUE | 2023-09-26 | YES | 2023-07-12 | FALSE |  | 2023-07-14 | TRUE | 2023-07-26 | TRUE | 2023-09-26 | X | TRUE |  | 2023-10-25 |  |  |  | 2023-07-26 | 2023-08-24 | 2023-08-24 |  | BOL# 11067 | 2023-07-26 | 2023-08-24 | 2023-09-12 | 2023-09-21 | 2023-09-25 | SEFL 32825601-3 / PRO 117505480
3 | 195 | TRUE | PR316239 | Sharnee Riley | 52 |  | 45 |  |  |  | 14 | 11-17 Install PO252681 - Need to send to vendor 11-17 Need to order straps 11/13/23 (JB): Pending installation schedule from Cardinal Concrete | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-06-09 | TRUE | 2023-09-26 | YES | 2023-06-15 | FALSE | 2023-07-27 | 2023-07-27 | TRUE | 2023-08-02 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-28 |  |  |  | 2023-08-04 | 2023-09-01 | 2023-08-24 |  | BOL# 11067 | 2023-08-04 | 2023-09-01 | 2023-09-07 | 2023-09-12 | 2023-09-15 | SEFL PRO 117422941
3 | 84 | TRUE | PR316157 | Sharnee Riley | 36 | [5 empty] | 3 | 11-17 Install PO252682 - need to send to vendor 11-17 Need to order straps 11/13/23 (JB): Pending installation schedule from Cardinal Concrete | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-06-16 | TRUE | 2023-09-26 | YES | 2023-06-20 | FALSE |  | 2023-07-25 | TRUE | 2023-08-02 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-28 |  |  |  | 2023-08-04 | 2023-09-01 | 2023-08-24 |  | BOL# 11067 | 2023-08-04 | 2023-09-01 | 2023-09-06 | 2023-09-12 | 2023-09-15 | SEFL PRO 117422941
4 | 104 | TRUE | PR316128 | JESSE BARRY | 13 |  | 10 |  |  |  | 5 | 11/13/23 (JB): Hardware order needs to be placed. | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-06-19 | TRUE | 2023-09-26 | YES | 2023-06-22 | FALSE | NA | 2023-06-30 | TRUE | 2023-07-05 | TRUE | 2023-09-26 | X | TRUE |  | 2023-08-28 |  |  |  | 2023-07-07 | 2023-08-04 | 2023-07-26 | 2023-07-27 | BOL# 11063B | 2023-07-07 | 2023-08-04 | 2023-08-31 | 2023-09-07 | 2023-09-11 | UPS: Box 1: 1Z4152380398686025; Box 2: 1Z4152380395883237 Box 3: 1Z4152380397123045
4 | 183 | TRUE | PR316229 | JESSE BARRY | 40 |  | 29 |  |  |  | 13 | 11/13/23 (JB): Hardware order needs to be placed. | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-06-29 | TRUE | 2023-09-26 | YES | 2023-07-06 | FALSE | 2023-07-20 | 2023-07-20 | TRUE | 2023-08-08 | TRUE | 2023-09-26 | X | TRUE |  | 2023-09-05 |  |  |  | 2023-08-08 | 2023-09-05 | 2023-08-24 |  | BOL# 11067 | 2023-08-08 | 2023-09-05 | 2023-09-12 | 2023-09-19 | 2023-09-22 | SEFL 31065168-9 / PRO 117482510
4 | 198 | TRUE | PR325986 | JESSE BARRY | 21 | [5 empty] | 1 | 11/13/23 (JB): Hardware order needs to be placed. | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-07-03 | TRUE | 2023-09-26 | YES | 2023-07-06 | FALSE | 2023-07-27 | 2023-07-25 | TRUE | 2023-08-08 | TRUE | 2023-09-26 | X | TRUE |  | 2023-09-05 |  |  |  | 2023-08-08 | 2023-09-05 | 2023-08-24 |  | BOL# 11067 | 2023-08-08 | 2023-09-05 | 2023-09-14 | 2023-09-19 | 2023-09-22 | UPS Box 1: 1Z4152380392813326 Box 2: 1Z4152380393548139 Box 3: 1Z4152380390915747
4 | 132 | TRUE | PR316165 | Kelly Stock | 58 |  | 8 |  |  |  | 14 | 8/7/23: Signs Ordered; Hardware request submitted | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-06-16 | TRUE | 2023-09-26 | YES | 2023-06-27 | FALSE |  | 2023-07-06 | TRUE | 2023-08-07 | TRUE | 2023-09-26 | X |  |  | 2023-09-05 |  |  |  | 2023-08-07 | 2023-09-05 | 2023-08-24 |  | BOL# 11067 | 2023-08-07 | 2023-09-05 | 2023-09-12 | 2023-09-19 | 2023-09-22 | SEFL 31065168-9 / PRO 117482510
4 | 192 | TRUE | PR316236 | Kelly Stock | 67 |  | 41 |  |  |  | 4 | 11/28/23: SO ready | MARTA APPROVED | WALTON - KELLY |  | 2023-09-14 | TRUE | 2023-09-26 | YES | 2023-09-22 | FALSE |  | 2023-10-09 | TRUE
4 | 856 | TRUE | PR316136 | Kelly Stock | 66 | [5 empty] | 22 | 9/7/23: Sign order placed w/vendor; need to order hardware | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-07-10 | TRUE | 2023-09-26 | YES | 2023-07-20 | FALSE |  | 2023-07-27 | TRUE | 2023-08-31 | TRUE | 2023-09-26 | X | [6 empty] | 2023-09-07 | 2023-10-06 | 2023-09-22 | 2023-09-22 | BOL# 1221179 | 2023-09-07 | 2023-10-06 | 2023-11-09 | 2023-11-09 | 2023-11-13 | PRO 117940950
4 | 172 | TRUE | PR316225 | Sharnee Riley | 120 | [5 empty] | 34 | 11-11-29 Sub Install PO252490 11-17 Need to order straps 11-17 Need to order Hardware 11-17 Signs and brackets ordered 9/25/23: Quote ready to be SO | SIGNS ORDERED | WALTON - KELLY | C. Robertson | 2023-07-12 | TRUE | 2023-09-26 | YES | 2023-07-13 | FALSE |  | 2023-09-13 | TRUE | 2023-09-26 | TRUE | 2023-09-26 | X | [6 empty] | 2023-09-26 | 2023-10-24 | 2023-10-16 | 2023-10-19 | BOL# 1229925 | 2023-09-26 | 2023-10-24 |  |  |  | HOLD AT MANUFACTUER PER PM
4 | 185 | TRUE | PR316230 | Sharnee Riley | 78 | [5 empty] | 23 | 11-17 Need to do install PO 11-17 Need to order straps 11-17 Need to order Hardware 11-17 Signs / brackets ordered 11/13/23 (JB): Hardware order needs to be placed. | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-07-27 | TRUE | 2023-09-26 | YES | 2023-07-30 | FALSE | 2023-07-20 | 2023-08-02 | TRUE | 2023-08-08 | TRUE | 2023-09-26 | X | TRUE |  | 2023-09-05 |  |  |  | 2023-08-08 | 2023-09-05 | 2023-09-05 | 2023-09-06 | 1Z8V2A750314295343 | 2023-08-08 | 2023-09-05 | 2023-09-20 | 2023-10-03 | 2023-10-06 | PRO 117607177
4 | 823 | TRUE | PR316169 | Sharnee Riley | 60 |  | 19 |  |  |  | 12 | 11-17 Need to do install PO 11-17 Need to order Uchannel 11-17 Need to order hardware 11/13/23 (JB): Hardware order needs to be placed. | SIGNS ORDERED | WALTON - JESSE | Cardinal Concrete | 2023-07-06 | TRUE | 2023-09-26 | YES | 2023-07-07 | FALSE | 2023-07-27 | 2023-07-19 | TRUE | 2023-08-08 | TRUE | 2023-09-26 | X | TRUE |  | 2023-09-05 |  |  |  | 2023-08-08 | 2023-09-05 | 2023-08-24 |  | BOL# 11067 | 2023-08-08 | 2023-09-05 | 2023-09-14 | 2023-09-25 | 2023-09-28 | PRO 117530743
4 | 850 | TRUE | PR316150 | Sharnee Riley | 74 | [5 empty] | 3 | 11-27 QT264356 and SO391201 completed 11-17 Need to complete all PO's 11/13/23 (JB): Route ready to be converted to SO. | MARTA APPROVED | WALTON - JESSE |  | 2023-08-11 | TRUE | 2023-09-26 | YES | 2023-08-03 | FALSE | 2023-08-10 | 2023-08-10 | TRUE
5 | 110 | TRUE | PR316131 | JESSE BARRY | 96 |  | 6 |  |  |  | 35 | 12-12 QT264345 and SO391559 completed * 11/13/23 (JB): Route approved on 9/7/23, but Emma requested updates on 10/27. Art updates required. 9/7/23 (LM): MARTA Approved | MARTA APPROVED | WALTON - JESSE |  | 2023-07-12 | TRUE | 2023-09-26 | YES | 2023-08-23 | FALSE | 2023-08-03 | 2023-09-07 | TRUE
5 | 124 |  | PR316159 | JESSE BARRY | 88 | [5 empty] | 14 | 12-26 QT 264430 and SO391775 completed * 11/13/23 (JB): Route ready to be converted to SO. | MARTA APPROVED | WALTON - JESSE |  | 2023-07-12 | TRUE | 2023-09-26 | YES | 2023-07-20 | FALSE | 2023-08-04 | 2023-08-04 | TRUE
5 | 27 |  | PR316248 | JESSE BARRY | 64 | [5 empty] | tbd | * 11/22/23 (JB): Revision 5 uploaded. Art approved per previous comment. | MARTA APPROVED | WALTON - JESSE |  | 2023-08-11 | TRUE | 2023-09-26 | YES | 2023-08-23 | FALSE | 2023-08-04 | 2023-09-07 | TRUE
5 | 120 | TRUE | PR316151 | Kelly Stock | 90 | [5 empty] | 17 | 11/6/23: Job cost transfer Bowstone PO to RT15 11/28/23: All product ordered | COMPLETE | WALTON - KELLY | Supreme | 2023-07-19 | TRUE | 2023-09-26 | YES | 2023-07-24 | FALSE |  | 2023-08-17 | TRUE | 2023-08-31 | TRUE | 2023-09-26 | X | TRUE |  | 2023-12-01 |  |  |  | 2023-09-13 | 2023-10-18 | 2023-09-22 | 2023-09-22 | BOL# 1221179 | 2023-09-13 | 2023-10-18 | 2023-11-16 | 2023-11-16 | 2023-11-20 | PRO 117995011 |  | 2023-11-16 |  |  | 2023-12-07 | 2023-12-07 | 2023-12-14
5 | 197 |  | PR325985 | Kelly Stock | 45 | [5 empty] | 4 | 11/28/23: SO ready | MARTA APPROVED | WALTON - KELLY |  | 2023-08-01 | TRUE | 2023-09-26 | YES | 2023-08-07 | FALSE |  | 2023-10-09 | TRUE
5 | 813 |  | PR316176 | Kelly Stock | 58 | [5 empty] | 3 | 11/28/23: SO ready | MARTA APPROVED | WALTON - KELLY |  | 2023-10-03 | TRUE | 2023-09-26 | YES | 2023-09-13 | FALSE |  | 2023-09-28 | TRUE
5 | 116 |  | PR316140 | Sharnee Riley | 108 | [5 empty] | 23 | 11-29 Sub Install PO 252487 - 11-20 Need to order Uchannel 11-20 Need to order straps 11-20 Need to order Hardware 9/7/23: Sign order placed w/vendor; | SIGNS ORDERED | WALTON - KELLY | C. Robertson | 2023-08-14 | TRUE | 2023-09-26 | YES | 2023-08-14 | FALSE |  | 2023-08-14 | TRUE | 2023-08-31 | TRUE | 2023-09-26 | X | [6 empty] | 2023-09-07 | 2023-10-06 | 2023-09-22 | 2023-09-22 | 1Z8V2A750305620187 | 2023-09-07 | 2023-10-06 | 2023-12-01 |  |  | HOLD AT MANUFACTUER PER PM
5 | 143 |  | PR316217 | Sharnee Riley | 35 |  | 18 |  |  |  | 5 | 11-20 Need to do INstall PO 11-20 Need to order Uchannel 11-20 Need to order straps 11-20 Need to order hardware 9/13/23: Signage ordered; | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-08-14 | TRUE | 2023-09-26 | YES | 2023-08-17 | FALSE |  | 2023-08-18 | TRUE | 2023-08-21 | TRUE | 2023-09-26 | X | [6 empty] | 2023-09-13 | 2023-10-20 | 2023-09-22 | 2023-09-22 | BOL# 1221179 | 2023-09-13 | 2023-10-20 | 2023-11-09 | 2023-11-09 | 2023-11-13 | PRO 117942014
5 | 50 |  | PR316199 | Sharnee Riley | 101 | [5 empty] | 28 | 12-26 QT264391 and SO391778 completed 11/22/23 (LM): MARTA approved | MARTA APPROVED | WALTON - JESSE |  | 2023-11-14 | TRUE | 2023-09-26 | YES | 2023-11-15 | FALSE | 2023-11-03 | 2023-11-22 | TRUE
5 | 85 |  | PR316154 | Sharnee Riley | 56 | [5 empty] | 17 | 12-27 Qt264359 and SO391801 completed * 11/13/23 (JB): Route ready to be converted to SO. | MARTA APPROVED | WALTON - JESSE |  | 2023-08-11 | TRUE | 2023-09-26 | YES | 2023-08-23 | FALSE | 2023-08-04 | 2023-09-07 | TRUE
6 | 125 |  | PR316161 | JESSE BARRY | 113 |  | 7 |  |  |  | 25 | 12-27 QT264364 and SO391802 completed * 11/13/23 (JB): Route ready to be converted to SO. | MARTA APPROVED | WALTON - JESSE |  | 2023-09-14 | TRUE | 2023-09-26 | YES | 2023-09-19 | FALSE | 2023-09-28 | 2023-09-28 | TRUE
6 | 133 |  | PR316168 | JESSE BARRY | 50 | [5 empty] | 3 | 12-27 QT264368 and SO391810 completed * 11/13/23 (JB): Route ready to be converted to SO. | MARTA APPROVED | WALTON - JESSE |  | 2023-08-15 | TRUE | 2023-09-26 | YES | 2023-08-23 | FALSE | 2023-09-12 | 2023-09-12 | TRUE
6 | 178 |  | PR316226 | JESSE BARRY | 50 | [5 empty] | 25 | 12/28/23 (JB): Route approved 12/8 | MARTA APPROVED | WALTON - JESSE |  | 2023-11-14 | TRUE | 2023-09-26 | YES | 2023-11-15 | FALSE | 2023-12-08 | 2023-12-08 | TRUE
6 | 103 |  | PR316126 | Kelly Stock | 70 |  | 12 |  |  |  | 6 | * 11/28/23: Need to order hardware | SIGNS ORDERED | WALTON - KELLY |  | 2023-08-14 | TRUE | 2023-09-26 | YES | 2023-08-17 | FALSE |  | 2023-09-07 | TRUE | 2023-09-26 | TRUE | 2023-09-26 | X | [6 empty] | 2023-09-26 | 2023-10-24 | 2023-10-16 | 2023-10-19 | BOL# 1229925 | 2023-09-26 | 2023-10-24 |  |  |  | HOLD AT MANUFACTUER PER PM
6 | 140 |  | PR316171 | Kelly Stock | 47 | [5 empty] | 14 | 11/28/23: Need to order hardware | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-08-02 | TRUE | 2023-09-26 | YES | 2023-08-07 | FALSE |  | 2023-08-18 | TRUE | 2023-09-26 | TRUE | 2023-09-26 | X | [6 empty] | 2023-09-26 | 2023-10-24 | 2023-09-27 | 2023-09-27 | HOLD AT MANUFACTURER | 2023-09-26 | 2023-10-24 | 2023-12-01 |  |  | HOLD AT MANUFACTUER PER PM
6 | 15 |  | PR316219 | Kelly Stock | 165 | [5 empty] | 46 | 12/19/23: w/art for revisions - due 12/21 11/6/23: See memo on PR when ordering signage | IN DESIGN FOR REVISION | WALTON - KELLY |  | 2023-12-19 | TRUE | 2023-09-26 | YES | 2023-11-14
6 | 87 |  | PR316127 | Kelly Stock | 82 |  | 18 |  |  |  | 35 | 11/28/23: Need to order hardware | SIGNS ORDERED | WALTON - KELLY | Cardinal Concrete | 2023-08-14 | TRUE | 2023-09-26 | YES |  | FALSE |  | 2023-09-08 | TRUE | 2023-09-26 | TRUE | 2023-09-26 | X | [6 empty] | 2023-09-26 | 2023-10-24 | 2023-10-16 | 2023-10-19 | BOL# 1229918 | 2023-09-26 | 2023-10-24 |  |  |  | HOLD AT MANUFACTUER PER PM
6 | 40 |  | PR316205 | Sharnee Riley | 65 |  | 15 |  |  |  | 2 | 12-27-23 QT264396 and SO391818 completed * 11/13/23 (JB): Route ready to be converted to SO. | MARTA APPROVED | WALTON - JESSE |  | 2023-08-25 | TRUE | 2023-09-26 | YES | 2023-10-16 | FALSE | 2023-09-28 | 2023-10-23 | TRUE
6 | 49 |  | PR316202 | Sharnee Riley | 102 | [5 empty] | 23 | * 11/13/23 (JB): Pending Marta review 10/16/23 (JB): Revision 8 uploaded for approval. It was revision 7, but we received feedback on some questions after R7 redlines were completed. 11/14/23 (EP): Approved by MARTA | MARTA APPROVED | WALTON - JESSE |  | 2023-09-21 | TRUE | 2023-10-16 | YES | 2023-10-16 | FALSE | 2023-11-14 | 2023-11-14 | TRUE
6 | 51 |  | PR316198 | Sharnee Riley | 82 |  | 12 |  |  |  | 9 | * 11-20 Create Quote and SO 11/14/23: Final art uploaded; Marta approved 10/6/23 (LM): Approved pending adjustments to 213101, 901115, 904547 | MARTA APPROVED | WALTON - KELLY |  | 2023-11-06 | TRUE | 2023-10-05 | YES | 2023-11-14 | FALSE |  | 2023-10-06 | TRUE
7 | 24 |  | PR316245 | JESSE BARRY | 166 | [5 empty] | 25 | 12/28/23 (JB): Route updated per approved as noted comments. | MARTA APPROVED | WALTON - JESSE |  | 2023-09-28 | TRUE | 2023-10-05 | YES | 2023-10-11 | FALSE | 2023-11-22 | 2023-11-22 | TRUE
7 | 34 |  | PR316211 | JESSE BARRY | 109 |  | 21 |  |  |  | 26 | * 11/13/23 (JB): Pending Marta review 10/18/23 (JB): Revision 2 uploaded for approval. | MARTA REVIEWING ART | MARTA |  | 2023-10-11 | TRUE | 2023-10-18 | YES | 2023-10-18 | FALSE
7 | 42 |  | PR316204 | JESSE BARRY | 98 |  | 25 |  |  |  | 25 | * 11/13/23 (JB): Pending Marta review 10/17/23 (JB): Revision 6 uploaded for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-12 | TRUE | 2023-10-17 | YES | 2023-10-17 | FALSE
7 | 142 |  | PR316216 | Kelly Stock | 26 | [5 empty] | 1 | 12/19/23: (KS) w/art for revision - due 12/21 12/11/23 (LM): Approved pending correction of 213287 PIP | IN DESIGN FOR REVISION | WALTON - KELLY |  | 2023-11-15 | TRUE | 2023-10-05 | YES | 2023-09-14 | FALSE | 2023-10-25 | 2023-12-11 | TRUE
7 | 155 |  | PR316222 | Kelly Stock | 88 |  | 33 |  |  |  | 7 | 11/7/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-17 | TRUE | 2023-10-05 | YES | 2023-11-07
7 | 55 |  | PR316197 | Kelly Stock | 131 | [5 empty] | 26 | 9/18/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-09-13 | TRUE | 2023-10-05 | YES | 2023-09-18
7 | 141 |  | PR316193 | Sharnee Riley | 68 | [5 empty] | 11 | * 11-20 Need to do Qt and SO 11-14 Revision completed 11/14/23: w/design for revision - due 11/16 11/14/23 (LM): MARTA approved pending revision to 903190 and 902775 | MARTA APPROVED | WALTON - KELLY |  | 2023-10-17 | TRUE | 2023-10-05 | YES | 2023-11-07 | FALSE |  | 2023-11-14 | TRUE
7 | 19 |  | PR316234 | Sharnee Riley | 122 | [5 empty] | 35 | 12/19/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-11-24 | TRUE | 2023-10-05 | YES | 2023-12-19 | FALSE | 2023-10-27
7 | 26 |  | PR316247 | Sharnee Riley | 89 | [5 empty] | 27 | * 12/4/23: (KS) Revision completed; uploading final art to SS; print files requested - due 12/7 | MARTA APPROVED | WALTON - KELLY |  | 2023-11-07 | TRUE | 2023-10-05 | YES | 2023-11-14 | FALSE |  | 2023-11-22 | TRUE
7 | 47 |  | PR316203 | Sharnee Riley | 77 | [5 empty] | 27 | * 12/4/23: (KS) Revision completed; uploading final art to SS; print files requested - due 12/7 | MARTA APPROVED | WALTON - KELLY |  | 2023-10-17 | TRUE | 2023-10-05 | YES | 2023-11-07 | FALSE |  | 2023-11-14 | TRUE
8 | 148 |  | PR316218 | JESSE BARRY | 36 |  | 2 |  |  |  | 7 | 12/28/23 (JB): Route updated per approved as noted comments. | MARTA APPROVED | WALTON - JESSE |  | 2023-12-19 | TRUE | 2023-10-19 | YES | 2023-10-19 | FALSE | 2023-12-11 | 2023-12-11 | TRUE
8 | 153 |  | PR316221 | JESSE BARRY | 18 |  | 35 |  |  |  | 1 | 12/28/23 (JB): Route updated per approved as noted comments. | MARTA APPROVED | WALTON - JESSE |  | 2023-12-19 | TRUE | 2023-10-18 | YES | 2023-10-18 | FALSE | 2023-12-11 | 2023-12-11 | TRUE
8 | 60 |  | PR316194 | JESSE BARRY | 81 |  | 3 |  |  |  | 33 | * 11/13/23 (JB): Pending Marta review 10/18/23 (JB): Revision 2 uploaded for approval. | MARTA REVIEWING ART | MARTA |  | 2023-10-11 | TRUE | 2023-10-18 | YES | 2023-10-18 | FALSE
8 | 93 |  | PR316119 | JESSE BARRY | 42 | [5 empty] | 2 | * 11/13/23 (JB): Pending Marta review 10/19/23 (JB): Revision 2 uploaded for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-16 | TRUE | 2023-10-19 | YES | 2023-10-19 | FALSE
8 | 25 |  | PR316246 | Kelly Stock | 42 | [5 empty] | 15 | 11/28/23: SO ready | MARTA APPROVED | WALTON - KELLY |  | 2023-11-14 | TRUE | 2023-10-05 | YES | 2023-09-18 | FALSE |  | 2023-10-27 | TRUE
8 | 68 |  | PR316188 | Kelly Stock | 105 |  | 51 |  |  |  | 26 | * 9/28/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-09-20 | TRUE | 2023-10-05 | YES | 2023-09-28
8 | 111 |  | PR316134 | Sharnee Riley | 104 |  | 51 |  |  |  | 37 | 12/11/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-12-04 | TRUE | 2023-10-05 | YES | 2023-09-14
8 | 30 |  | PR316213 | Sharnee Riley | 99 |  |  | TRUE |  |  | 12 | 12/19/23: (KS) uploaded final art - ready to be SO | MARTA APPROVED | WALTON - SHARNEE |  | 2023-11-06 | TRUE | 2023-10-05 | YES | 2023-09-28 | FALSE | 2023-11-22 | 2023-11-22 | TRUE
8 | 58 |  | PR316196 | Sharnee Riley | 110 |  | 27 |  |  |  | 29 | 12/19/23:(KS) w/design for revision - due 12/22 | IN DESIGN FOR REVISION | WALTON - JESSE |  | 2023-12-19 | TRUE | 2023-10-17 | YES | 2023-10-17 | FALSE
8 | 86 |  | PR316133 | Sharnee Riley | 111 |  | 42 |  |  |  |  | * 11/13/23 (JB): Pending Marta review 10/25/23 (JB): Revision 2 uploaded for approval. | MARTA REVIEWING ART | MARTA |  | 2023-10-19 | TRUE | 2023-10-25 | YES | 2023-10-25 | FALSE
9 | 123 |  | PR316156 | JESSE BARRY | 7 | [6 empty] | * 11/13/23 (JB): Pending Marta review 10/25/23 (JB): Revision 2 uploaded for approval. | MARTA REVIEWING ART | MARTA |  | 2023-10-19 | TRUE | 2023-10-25 | YES | 2023-10-25 | FALSE
9 | 150 |  | PR316220 | JESSE BARRY | 51 | [5 empty] | 24 | *11/14/23 (JB): Revision 3 uploaded for Marta approval | MARTA REVIEWING ART | MARTA |  | 2023-10-23 | TRUE | 2023-11-14 | YES | 2023-11-14 | FALSE
9 | 189 |  | PR316233 | JESSE BARRY | 82 | [6 empty] | *11/14/23 (JB): Revision 2 uploaded for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-27 | TRUE | 2023-11-14 | YES | 2023-11-14 | FALSE
9 | 81 |  | PR316177 | JESSE BARRY | 152 |  | 30 |  |  |  | 53 | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE | [6 empty] | FALSE
9 | 853 |  | PR316147 | JESSE BARRY | 56 | [5 empty] | 9 | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE | [6 empty] | FALSE
9 | 188 |  | PR316232 | Kelly Stock | 22 | [5 empty] | 11 | *10/10/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-03 |  | 2023-10-10
9 | 66 |  | PR316192 | Sharnee Riley | 132 |  | 29 |  |  |  | 42 | *10/6/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-03 |  | 2023-10-06
9 | 75 |  | PR316183 | Sharnee Riley | 75 | [6 empty] | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE | [6 empty] | FALSE
9 | 825 |  | PR316167 | Sharnee Riley | 25 | [6 empty] | *11/13/23 (JB): Pending Marta review 10/25/23 (JB): Revision 2 uploaded for approval. | MARTA REVIEWING ART | MARTA |  | 2023-10-19 | TRUE | 2023-10-25 | YES | 2023-10-25 | FALSE
9 | 94 |  | PR316118 | Sharnee Riley | 35 |  | 16 |  |  |  | 7 | 12/11/23: w/art for revision - due 12/13 | MARTA APPROVED | WALTON - KELLY |  | 2023-12-11 |  | 2023-10-17 |  |  | FALSE |  | 2023-11-22 | TRUE
10 | 1 |  | PR316110 | JESSE BARRY | 60 |  | 13 |  |  |  | 14 | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE | [6 empty] | FALSE
10 | 114 |  | PR316137 | JESSE BARRY | 92 | [6 empty] | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE | [6 empty] | FALSE
10 | 14 |  | PR316170 | Kelly Stock | 55 | [6 empty] | *10/18/23: Uploaded R2 for Marta approval | MARTA REVIEWING ART | MARTA |  | 2023-10-06 |  | 2023-10-18
10 | 74 |  | PR316184 | Kelly Stock | 87 | [5 empty] | 19 | *10/18/23: Uploaded R2 for Marta approval | MARTA REVIEWING ART | MARTA |  | 2023-10-09 |  | 2023-10-18
10 | 809 |  | PR316178 | Kelly Stock | 82 | [5 empty] | 19 | *11/7/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-25 |  | 2023-11-07
10 | 9 |  | PR316122 | Kelly Stock | 88 |  | 26 |  |  |  | 19 | *12/4/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-11-20 |  | 2023-12-04
10 | 126 |  | PR316164 | Sharnee Riley | 85 | [5 empty] | 25 | *10/18/23: Uploaded R2 for Marta approval | MARTA REVIEWING ART | MARTA |  | 2023-10-05 |  | 2023-10-18
10 | 8 |  | PR316180 | Sharnee Riley | 113 | [5 empty] | 26 | *11/6/23: W/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-19 |  | 2023-11-06
10 | 832 |  | PR316160 | Sharnee Riley | 47 | [6 empty] | *11/7/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-27 |  | 2023-11-07
10 | 867 |  | PR316130 | Sharnee Riley | 57 |  | 58 |  |  |  | 24 | *11/7/23: w/Marta for approval | MARTA REVIEWING ART | MARTA |  | 2023-10-27 |  | 2023-11-07
11 | 165 |  | PR316224 | JESSE BARRY | 64 | [6 empty] | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE
11 | 36 |  | PR316210 | JESSE BARRY | 90 | [6 empty] | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE
11 | 4 |  | PR316206 | JESSE BARRY | 109 | [5 empty] | 46 | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE
11 | 71 |  | PR316187 | JESSE BARRY | 89 | [5 empty] | 13 | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE
11 | 295 |  | PR316249 | Kelly Stock | 2 | [5 empty] | 1 | *11/27/23: KB and LS to get visual of stop prior to going to art | REVIEWING ROUTES FOR REVISIONS | WALTON - KELLY
11 | 32 |  | PR316212 | Kelly Stock | 90 | [5 empty] | 9 | *12/11/23: w/art for revisions - due 12/13 | IN DESIGN FOR REVISION | WALTON - KELLY |  | 2023-12-11
11 | 6 |  | PR316195 | Kelly Stock | 118 | [5 empty] | 14 | *12/11/23: w/art for revisions - due 12/14 | IN DESIGN FOR REVISION | WALTON - KELLY |  | 2023-12-11
11 | 79 |  | PR316181 | Kelly Stock | 72 |  | 21 |  |  |  | 9 | *11/27/23: Need R1 run through Sherlock prior to requesting art revision | REVIEWING ROUTES FOR REVISIONS | WALTON - KELLY
11 | 102 |  | PR316121 | Sharnee Riley | 42 |  | 9 |  |  |  | 22 | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE
11 | 2 |  | PR316241 | Sharnee Riley | 37 | [5 empty] | 5 | *11/27/23: Need R1 run through Sherlock prior to requesting art revision | REVIEWING ROUTES FOR REVISIONS | WALTON - KELLY
11 | 37 |  | PR316209 | Sharnee Riley | 56 |  | 8 |  |  |  | 7 | *11/27/23: Need R1 run through Sherlock prior to requesting art revision | REVIEWING ROUTES FOR REVISIONS | WALTON - KELLY
11 | 816 |  | PR316173 | Sharnee Riley | 93 | [6 empty] | *11/13/23 (JB): Walton PM needs to review art for revisions and update the install conditions. | REVIEWING ROUTES FOR REVISIONS | WALTON - JESSE
11 | 899 |  | PR316124 | Sharnee Riley | 22 | [5 empty] | 2 | *11/27/23: Need R1 run through Sherlock prior to requesting art revision | REVIEWING ROUTES FOR REVISIONS | WALTON - KELLY